## Sheet2
[15 empty] | 183 | 228 | 268 | 306 | 403 | 4704 | 6092 | 101.5333
Order | Base Release | Base Release Service Pack (SP) | Custom Release | Dictionary Release | Rules Flat File | Edit Clarifications Release | TPIC Release | TPIC Metadata .XML files Release | Custom Rules EXport (internal) | Custom Rules IMport (internal) | Action | Applies to: | BOIP ACTION | BOIP Expected Result | Minutes to Deploy to 3D | Minutes to Deploy to 7D | Minutes to Deploy to 1E | Minutes to Deploy to 8Q | Minutes to Deploy to 1P | Avg. Minutes to Deploy to each Backflush env. | Total Mins | Total Deployment hours
4 | y | y | y | y | y | y | y | y | n | y | Inform APM to stop monitoring CXT alerts | whole environment | Email APM, asking them to stop monitoring alerts for CXT* until mm/dd/yy/ hh:mm | all nodes inactive | 0 | 0 | 2 | 2 | 2 | 0
5 | y | y | y | y | y | y | y | y | n | y | Run CXT healthcheck to ensure no existing problems | whole environment | VALIDATE TPIC Adjudication is functional (steps 1-10) | no errors found | 3 | 3 | 3 | 3 | 5 | 3
6 | y | y | y | y | y | y | y | y | n | y | Update RM spreadhsheet the change effort had begin | whole environment | Status Master Input Link | spreadsheet updated | 0 | 0 | 0 | 0 | 5 | 3
7 | y | y | y | y | y | y | y | y | n | y | Verify Reporting servicer services | Reporting | Run Reporting Server Pre-Checks |  | 0 | 5 | 0 | 5 | 5 | 0
8 | y | y | y | y | y | y | y | y | n | y | Disable loadbalanced services (TPIC) if they exist | whole environment | Suspend all nodes from TPIC load balancer | all nodes inactive | 0 | 0 | 0 | 5 | 5 | 0
9 | y | y | y | y | y | y | n | n | n | y | Disable loadbalanced services (TPPUI) if they exist | whole environment | Suspend all nodes from TPPUI load balancer | all nodes inactive | 0 | 0 | 0 | 5 | 5 | 0
10 | y | y | y | y | y | y | n | n | n | y | Disable loadbalanced services (UIAPP) if they exist | whole environment | Suspend all nodes from UIAPP load balancer | all nodes inactive | 0 | 0 | 0 | 5 | 5 | 0
11 | y | y | y | y | y | y | n | n | n | y | Disable loadbalanced services (C3) if they exist | whole environment | Suspend all nodes from C3 load balancer | all nodes inactive | 0 | 0 | 0 | 5 | 5 | 0
12 | y | y | y | y | y | y | y | n | n | y | Stop UIAPP and TPIC Services | UIAPP and TPIC | Stop UIAPP and TPIC CXT services in environment(s) using EMT GUI | services stopped | 3 | 3 | 5 | 5 | 5 | 3
13 | y | y | y | y | y | y | y | y | y | y | Archive or Delete existing CXT log files | TPIC only | Archive or Delete the existing CXT logs | Files archived or deleted | 5 | 5 | 5 | 5 | 5 | 5
15 | y | y | y | n | n | n | y | n | n | n | Backup Config files | all servers except Reporting | Backup Config files | Files backed up | 5 | 5 | 10 | 10 | 10 | 5
16 | n | n | n | n | n | n | y | n | n | n | Backup Config files | TPIC Only | Backup Config files | Files backed up | 5 | 5 | 10 | 10 | 10 | 5
20 | y | n | n | n | n | n | n | n | n | n | Uninstall Base Release | all servers | DOCUMENT DOES NOT EXIST | Base application removed | 5 | 10 | 5 | 5 | 5 | 5
25 | y | n | n | n | n | n | n | n | n | n | Install Base Release | all servers | Install Base Release | Base application installed | 10 | 15 | 20 | 20 | 20 | 10
30 | y | y | y | n | n | n | n | n | n | n | Uninstall Custom Release | all servers | Uninstall Custom Release | Custom application removed | 10 | 15 | 15 | 15 | 15 | 10
32 | n | y | n | n | n | n | n | n | n | n | Install Service Pack | all servers | Install Service Pack | Service Pack installed | 10 | 15 | 15 | 15 | 15 | 10
35 | y | y | y | n | n | n | n | n | n | n | Install Custom Release | all servers | Install Custom Release | Custom Application installed | 10 | 15 | 15 | 15 | 15 | 10
40 | n | n | n | n | y | n | n | n | n | n | Import Rules Flat File | one UIAPP per env. EXCEPT DR | Install Rules Flat File | Rules imported | 5 | 5 | 15 | 15 | 15 | 5
45 | n | n | n | n | y | n | n | n | n | n | IF LISTED IN CHC RELEASE NOTES: Deactivate out-of-the-box rules (may be 3D and 7D only, but release-specific) | one UIAPP per env. | IF LISTED IN CHC RELEASE NOTES: Deactivate out-of-the-box rules (may be 3D and 7D only, but release-specific) | Rules deactivated | 5 | 5 | n/a | n/a | n/a | n/a
50 | n | n | n | n | n | y | n | n | n | n | Install Edit Clarifications | one UIAPP per env. EXCEPT DR | Import Edit Clarifications | Edits installed | 15 | 15 | 15 | 15 | 15 | 15
60 | y | y | y | y | n | n | n | n | n | n | Install New Dictionary | UIAPP and TPIC | Install new dictionary file | File installed | 5 | 5 | 10 | 10 | 15 | 5
70 | n | n | n | n | n | n | y | n | n | n | Uninstall TPIC Facets Application | TPIC | Uninstall TPIC Facets Application | TPIC Facets application removed | 5 | 5 | 15 | 15 | 15 | 5
75 | n | n | n | n | n | n | y | n | n | n | Install TPIC Facets Application | TPIC | Install TPIC Facets Application | TPIC Facets application installed | 5 | 5 | 10 | 10 | 10 | 5
80 | n | n | n | n | Y | n | n | n | y | y | Import/Compare Custom Rules (everywhere EXCEPT 3-D and 7-D) | one UIAPP per env. EXCEPT DR | Import custom rules | Rules imported | 0 | 0 | 5 | 5 | 5 | 5
90 | n | y | y | n | n | n | y | n | n | n | Replace Config Files | all servers except Reporting | Replace Config Files | Files replaced | 5 | 5 | 5 | 5 | 5 | 5
92 | y | y | y | n | n | n | n | n | n | n | Edit Nthost config files | UIAPP and TPIC | Edit Nthost config files | files edited | 5 | 5 | 5 | 5 | 5 | 5
93 | y | n | n | n | n | n | y | n | n | n | Edit Web.Config Files | TPIC | Edit Web.Config Files | files edited | 5 | 5 | 5 | 5 | 5 | 5
94 | y | y | y | n | n | n | n | n | n | n | Edit Web.Config Files | TPPUI, C3 | Edit Web.Config Files | files edited | 5 | 5 | 5 | 5 | 5 | 5
96 | n | n | n | n | n | n | y | n | n | n | Edit TPIC.config files | TPIC | Edit TPIC.config files | files edited | 5 | 5 | 5 | 5 | 5 | 5
100 | n | n | n | n | n | n | y | y | n | n | Install TPIC metadata .XML files | TPIC | Install most current metadata files | files installed | 5 | 5 | 5 | 5 | 5 | 5
130 | y | y | y | n | n | n | n | n | n | n | Set LDAP manager password | TPPUI, UIAPP | Set LDAP manager password | Password set | 5 | 5 | 5 | 5 | 5 | 5
135 | n | n | n | n | n | n | n | n | n | n | Set Crystal Report server password on UIAPP servers - no longer needed | UIAPP if environment has reporting server | Set Crystal Report server password on UIAPP servers | Password set | n/a | n/a | n/a | n/a | n/a | n/a
150 | n | n | n | n | n | n | n | n | n | n | Set TPIC manager password no longer needed | TPIC | (no longer needed because we do not use the LDAP password with TPIC) |  | n/a | n/a | n/a | n/a | n/a | n/a
160 | y | y | y | y | y | y | y | n | y | y | Start UIAPP and TPIC Services | UIAPP and TPIC | Start UIAPP and TPIC CXT services in environment(s) using EMT GUI | Services started | 7 | 7 | 10 | 10 | 10 | 7
185 | y | y | y | y | n | n | n | n | n | n | Perform IISreset/restart all CXT webservices | all servers | Perform IIS reset | IIS restarted | 5 | 5 | 7 | 7 | 7 | 5
186 | n | n | n | n | n | y | y | y | n | n | Perform IISreset/restart all CXT webservices | TPIC servers | Perform IIS reset | IIS restarted | 5 | 5 | 7 | 7 | 7 | 5
190 | y | y | y | y | y | y | y | n | n | y | Re-enable loadbalanced services (TPIC) if they exist | whole environment | Activate all nodes from TPIC load balancer | all nodes activated | 0 | 0 | 0 | 0 | 5 | 0
191 | y | y | y | y | y | y | n | n | n | y | Re-enable loadbalanced services (TPPUI) if they exist | whole environment | Activate all nodes from TPPUI load balancer | all nodes activated | 0 | 0 | 0 | 0 | 5 | 0
192 | y | y | y | y | y | y | n | n | n | y | Re-enable loadbalanced services (UIAPP) if they exist | whole environment | Activate all nodes from UIAPP load balancer | all nodes activated | 0 | 0 | 0 | 0 | 5 | 0
193 | y | y | y | y | y | y | n | n | n | y | Re-enable loadbalanced services (C3) if they exist | whole environment | Activate all nodes from C3 load balancer | all nodes activated | 0 | 0 | 0 | 0 | 5 | 0
300 | y | y | y | y | y | y | n | y | y | y | Validate UIAPP services/WSDL's | UIAPP and UIAPP VIP | Validate UIApp and TPIC services using EMT GUI | URLs validate successfully | 5 | 5 | 5 | 5 | 5 | 5
305 | y | y | y | y | y | y | y | y | y | y | Validate TPIC services/WSDL's | TPIC and TPIC VIP | Validate UIApp and TPIC services using EMT GUI | URLs validate successfully | 5 | 5 | 5 | 5 | 5 | 5
310 | y | y | y | y | y | y | y | y | y | y | Validate TPPUI login | TPPUI and TPPUI VIP | Validate TPPUI Server | Able to log into TPPUI | 5 | 5 | 5 | 5 | 5 | 5
315 | y | y | y | y | y | y | y | y | y | y | Validate TPIC adjudication on TPIC servers | TPIC except DR | VALIDATE TPIC Adjudication is functional (steps 1-10) | Clean healthcheck | 5 | 5 | 5 | 5 | 5 | 5
320 | y | y | y | y | y | y | y | y | y | y | Validate Claims Adjudication through Facets | TPIC via Facets | VALIDATE Claims Adjudication (F3) is functional (step 11 only) | F3 of claims successful and claims show up in TPPUI | 5 | 5 | 5 | 5 | 5 | 5
325 | y | y | y | y | y | y | n | y | y | y | Validate C3 services | C3 and C3 VIP | VALIDATE C3 Services are functional | SERVICES FUNCTIONAL | 0 | 5 | 0 | 5 | 10 | 0
330 | y | y | y | n | n | n | n | n | n | n | Validate Reporting Server | Reporting | VALIDATE Reporting server is functional | SERVICES FUNCTIONAL | 0 | 5 | 0 | 5 | 5 | 0
340 | y | y | y | y | y | y | y | y | y | y | Perform App Compare | ALL | Perform App Compares using the templates in \\va01dfacapp971\d$\Scripts\CXT_COMPARE_TEST\Launchers (run as admin, provide master and target environments when prompted): 1) TPIC: Master to current_env_upgrading 2) UIAPP: Master to current_env_upgrading 3) TPPUI: Master to current_env_upgrading 4) C3: Master to current_env_upgrading 5) Reporting: Master to current_env_upgrading 6) TPIC: current_env_upgrading to itself 7) UIAPP: current_env_upgrading to itself 8) TPPUI: current_env_upgrading to itself 9) C3: current_env_upgrading to itself *** 3D master for 7D 7D master for 8Q 8Q master for everything else | no discrepancies | 0 | 5 | 7 | 10 | 10 | 10
400 | y | y | y | y | y | y | y | y | y | y | Validate Environment (Code Editing) | ALL | Validate Environment | ENVIRONMENT FUNCTIONAL | n/a | n/a | n/a | n/a | n/a | n/a
420 | y | y | y | y | y | y | y | y | y | y | Send Broadcast when work is complete | ALL | Send Broadcast when work is complete | broadcast sent | n/a | n/a | n/a | n/a | 10 | n/a
415 | y | y | y | y | y | y | y | y | y | y | Inform Claims Team that they can release CLMU | ALL | Inform Claims Team that they can release CLMU | phonecall made | n/a | n/a | n/a | n/a | 5 | n/a
420 | y | y | y | y | y | y | y | y | y | y | Close deployment and validation tasks in SNOW | ALL | Close deployment and validation tasks in SNOW | tasks closed | n/a | n/a | n/a | n/a | 9 | n/a
425 | y | y | y | y | y | y | y | y | y | y | Close SNOW CHG | ALL | Close SNOW CHG | CNR closed | n/a | n/a | n/a | n/a | 1 | n/a
| y | y | y | y | y | y | y | y | n | y | Inform APM to resume monitoring CXT alerts | whole environment | Email APM, asking them to resume monitoring CXT* alerts | all nodes inactive | 0 | 0 | 2 | 2 | 2 | 0
| y | y | y | y | y | y | y | y | n | y | update RM spreadsheet that change is complete | whole environment | Status Master Input Link | spreadsheet updated | 0 | 0 | 0 | 0 | 5 | 0
430 | y | y | y | y | y | y | y | y | y | y | Perform the Ready-For-Business email the day after implementation to PROD | ALL | Perform the Ready-For-Business email the day after implementation to PROD: https://share.antheminc.com/teams/AppEnvrMgmt/trizettosupport/Shared%20Documents/ClaimsXten/Procedures/How-to%20Docs/How_To_Send_Ready_For_Business_Validation_After_McKesson_Outage.docx?Web=1 | Email sent | n/a | n/a | n/a | n/a | 30 | n/a
435
`

## Sheet3
0.049438
0.049413
0.049104